## IO_Layout
Board	Port	Wire #	Device	Breaker Size	Breaker Number
Analog Breakout	1		Ultrasonic sensor	20 AMP
	2		Gyro Sensor
	3		Spare
	4		Spare
	5		Spare
	6		Spare
	7		Spare
	8		Spare

Digital Sidecar - PWM Outputs	1	88	Rear Left Motor	40 amp
	2	86	Rear Right Motor	40 amp
	3	93	Front Left Motor	40 amp
	4	56	Front Right Motor	40 amp
	5	65	accq rollor motor	20 amp
	6	89 90	Shooter winch motor	40 amp
	7	94	Shooter shoulder	20 AMP
	8	87	Hardstop motor	20 AMP
	9	6	Winch Gearbox shifter	sidecar power
	10	81	Latch motor	sidecar power

Digital Sidecar - Relay Outputs	1		Spare
	2		Spare
	3		Spare
	4		Spare
	5		Spare
	6		Spare
	7		Spare
	8		Spare

Digital Sidecar - Digital I/O	1		Spare
	2		Reload sensor
	3		Encoder Source A - Shooter
	4		Encoder Source B - Shooter
	5		Accq top sensor
	6		Accq Bottom sensor
	7		Shooter latch sensor top
	8		Shooter latch sensor bottom
	9		Spare
	10		Spare
	11		Spare
	12		Spare
	13		Spare
	14		Spare

Digital Sidecar - Outputs	1		Spare
	2		Spare
	3		Spare
	4		Spare

## STATIC_-_Robot
Item	Test Procedure	Tools	Acceptance Criteria	Results	OK / NOT OK	Action Required/comments
1	Check that all wires labeled	Visual	All Labels Present
2	Check that all devices are labeled	Visual	All Labels Present
3	Check that Devices matched to correct ports	Visual, Drawings	As per drawing
4	Check that all cables/wires exposed to non-moving parts	Visual, Drawings	Compliance
5	Check for appropriate slack on any moving components	Visual, Drawings	Compliance
6	Check for appropriate connectors (female on power end male on device end).	Visual, Drawings	Compliance
7	Check for Debris on Control Panel	Visual	No dust/ debris/ metal chips
8	Check wire termination tightness on the terminal blocks. (control & power)	Hand	Not loose
9	Check that only one wire is connected to any terminal.	Visual	As per spec.
10	Check that exposed terminals are covered with electrical tape or other insulating material.	Visual	As per spec.
11	Check that all electrical components are securely mounted to sub-panel.	By hand, look for loose screws, etc	Not loose
12	Check for any damaged electrical components.	Visual	No damage
13	Check Ethernet plug tightness. If applicable	By hand	Not loose
14	Check that Main Disconnect is accessible	Visual	Compliance
15	Check that the Pneumatic Relief Valve is Accessible	Visual	Compliance
16	Check that the High Pressure and Low Pressure Gauges are visible	Visual	Compliance
17	Check that Correct Snap Action Breaker sizes are inserted	Visual	As per spec.
18	Check that proper AWG wires are being used based on load.	Visual	As per spec.

## DYNAMIC_-_Robot
Item	Test Procedure	Tools	Acceptance Criteria	Results	OK / NOT OK	Action Required/comments
1	Set of prints to yellow line.	Visual	Completed
2	Safety must be the number one priority during the dynamic phase of the VAT. Ensure that safe practices are used during these tests. Pneumatic power should be LOCKED OUT during any modifications to the Module.	Visual	Completed
3	Verify safety valve operations.	Visual	Operation passes
4	Verify incoming air supply.	Visual	Operation passes
5	Verify incomming regulator setting.	Visual	Setting as per drawings
6	Verify field device regulator setting.	Visual	Setting as per drawings
7	Check for leaks.	Visual, Audible	No leaks
8	Check that all pneumatic solenoid valves are de-energized and exhausted when the air & power disconnects are in the OFF position.	Visual	As per spec
9	Verify operation of Relief valve should pressure switch fail	Visual	As per spec
10	Verify Machine is not grounded (connected negative terminal to frame via Multimeter)	Multimeter	< 5 Ohms
11	Remove Breakers and verify voltage	Multimeter	12VDC
12	Install Breakers and verify voltage	Multimeter	12VDC on each breaker
13	Verify all devices have Power	Visual	Power present on all devices
14	Verify Solenoid Outputs by triggering device and checking for correct state change - Shooter Extend	Laptop	All devices test pass
15	Verify Solenoid Outputs by triggering device and checking for correct state change - Shooter Retract	Laptop	All devices test pass
16	Verify Solenoid Outputs by triggering device and checking for correct state change - Shooter Stop Oin Extend	Laptop	All devices test pass
17	Verify Solenoid Outputs by triggering device and checking for correct state change - Shooter Stop Oin Retract	Laptop	All devices test pass
18	Verify Solenoid Outputs by triggering device and checking for correct state change - Level 1 Climb Extend	Laptop	All devices test pass
19	Verify Solenoid Outputs by triggering device and checking for correct state change - Level 1 Climb Retract	Laptop	All devices test pass
20	Verify Solenoid Outputs by triggering device and checking for correct state change - Shooter Fire Extend	Laptop	All devices test pass
21	Verify Solenoid Outputs by triggering device and checking for correct state change - Shooter Fire Retract	Laptop	All devices test pass
22	Verify Digital Sidecar PWM Outputs by triggering device and checking for correct state change - Left Side Drive	Laptop	All devices test pass
23	Verify Digital Sidecar PWM Outputs by triggering device and checking for correct state change - Right Side Drive	Laptop	All devices test pass
24	Verify Digital Sidecar PWM Outputs by triggering device and checking for correct state change - Shooter Wheel	Laptop	All devices test pass
25	Verify Digital Sidecar PWM Outputs by triggering device and checking for correct state change - Shooter Lid	Laptop	All devices test pass
26	Verify Digital Sidecar PWM Outputs by triggering device and checking for correct state change - Winch	Laptop	All devices test pass
27	Verify Digital Sidecar PWM Outputs by triggering device and checking for correct state change - Shooter Lift Stop	Laptop	All devices test pass
28	Verify Digital Sidecar Relay Outputs by triggering device and checking for correct state change - Compressor	Laptop	All devices test pass
29	Verify Digital Sidecar Relay Outputs by triggering device and checking for correct state change - Shifters	Laptop	All devices test pass
30	Verify Digital Sidecar Relay Outputs by triggering device and checking for correct state change - Red/Blue Alliance Lights	Laptop	All devices test pass
31	Verify Digital Sidecar Relay Outputs by triggering device and checking for correct state change - Shooter Wheel at Speed Light	Laptop	All devices test pass
32	Verify Digital Sidecar Digital I/O by triggering device and checking for correct state change - Pressure Switch	Laptop	All devices test pass
33	Verify Digital Sidecar Digital I/O by triggering device and checking for correct state change - Encoder	Laptop	All devices test pass

## SHOP_COMPLETION_LIST
Item	Area	Description	Next Steps	Priority	Estimated / StartEstimated / Start	Estimated / CompletionEstimated / Completion	Date Completed	Comments	Elec.Draw. / Page #Elec.Draw. / Page #
EX	Digital Side Car	Power Wires not connected	Installed Power wires	1	2/25/2013	2/25/2013	2/25/2013	Installed missing Power wires, 18awg red and black from terminal 92 using a 20 amp snap action breaker	20
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20